## Agile Project Plan
Flashcard Academy Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Have a deployed flashcard application which utilizes a spaced repetition algorithm to allow users to study and test their knowledge of software engineering concepts.
| Flashcard Academy | Zach M. | 2018-11-19 | 2018-01-01 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Build Flashcard Models |  | Zach M. |  | 2018-11-26 | 2018-11-30 | 4 | In Progress
| Create Associations |  |  |  | 2018-11-26 | 2018-11-30 | 4 | In Progress
| Build Quiz Front End |  |  |  | 2018-11-26 | 2018-11-30 | 4 | Not Started
| Build Quiz Backend |  |  |  | 2018-11-26 | 2018-11-30 | 4 | Not Started
| Build Click on Card Function |  |  |  | 2018-12-03 | 2018-12-07 | 4 | Not Started
| Implement Spaced Repetition Algorithm |  |  |  | 2018-11-26 | 2018-11-30 | 4 | Not Started
| Build Questions Front End |  |  |  | 2018-12-03 | 2018-12-07 | 4 | Not Started
| Build Questions Back End |  |  |  | 2018-12-03 | 2018-12-07 | 4 | Not Started
0
0
0
0

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## Settings
Status | Overall Progress
Not Started | 0%
In Progress | 5%
Completed | 10%
Overdue | 15%
20%
25%
30%
35%
40%
45%
50%
55%
60%
65%
70%
75%
80%
85%
90%
95%
100%